Accessibility Inclusion Action Plan 2020-23

Dated

November 2020

DOCUMENT CONTROL

|  | Report Template - Business Support |
| --- | --- |
| Custodian | Diversity & Learning Officer |
| Approver | Executive – People & Resilience |
| Status | Final |
| Version | 1 |
| Approved Date | 3/12/2020 |
| Review Due Date | 4/12/2023 |

© Wannon Region Water Corporation

PO Box 1158

Warrnambool 3280

# Contents

Contents	3

1.0	Message from the MD	4

2.0	Purpose of this Plan	4

3.0	Governance and Accountability	5

3.1	Tracking and Progress Reporting	5

4.0	Implementation	5

5.0	Legislative Framework	6

6.0	Outcomes and Activities	7

Outcome 1: Provide services and facilities that are accessible to all	7

Outcome 2: Reducing barriers to people with disability obtaining and maintaining employment with Wannon Water	9

Outcome 3: Promoting inclusion and participation in the community of people with disability	9

Outcome 4: Achieve organisational culture change in attitudes and practices which discriminate against disability	10

7.0	Glossary	12

8.0	Reference Documents	12

# Message from the MD

Wannon Water is central to the economy and community of south-west Victoria. We take great pride in our historic role of delivering essential water and sewerage services to our customers and we recognise our business can have far-reaching impacts.

Inclusion and diversity is at the heart of our organisation for our employees, customers and our broader community. There is no one aspect that is more important than another.

Inclusion and diversity is widely supported throughout our organisation with a Committee that provides advice to the executive committee and People & Wellbeing team. Employees from across the organisation assist the committee to implement the actions of the Inclusion and Diversity Management Plan and any additional work plans and activities.

A variety of internal and external stakeholders have had input into the development of our plans that support our organisation and broader community. This includes working with local indigenous groups to complete a Reconciliation Action Plan, providing a Financial Inclusion Action Plan for our customers, and, developing this Accessibility Inclusion Plan. Our approach towards accessibility reflects the Social Model of Disability, where we acknowledge that it is often society’s attitudes, systems and constructs, rather than a person’s impairment that can be restrictive.

# Purpose of this Plan

Wannon Water prides itself on being a fair and equitable workplace. Our vision for an accessible business includes: having sites and amenities that are accessible, employing an inclusive workforce and creating a respectful and understanding culture, and, reflecting and supporting our community.

The Wannon Water People & Culture Policy statement informs our Inclusion and Diversity management plan (and any sub-plans) to take a systematic approach towards inclusion and diversity initiatives. The Management Plan (and any sub-plans) provides a level of structure, resources and governance to assist the implemented activities to achieve our intended organisational outcomes, including those outlined in this Accessibility Inclusion Action Plan.

The Accessibility Inclusion Action Plan (the Plan), is an organisational wide internal management plan that supports the Inclusion & Diversity Management Plan and specific approach to advancing our progress on Accessibility.

# Governance and Accountability

This Plan will support our systematic approach to implementing the Inclusion and Diversity Management Plan and will be measured annually as part of the Inclusion and Diversity reporting cycle. The levels of accountability related to our Inclusion and Diversity portfolio is as follows:

## Tracking and progress reporting

| Action | Task | Timeline | Responsibility |
| --- | --- | --- | --- |
| Report annually on achievements | Assessment and update of this plan is undertaken | September | Executive Risk and Resilience |
| Report back to the Inclusion and Diversity Committee on the achievements of our actions | Reports provided to Accessibility Working Group and Inclusion & Diversity Committee on achievements to date | Quarterly | Diversity & Learning Officer |
| Review and develop a new DIAP | Review and develop future DIAP’s | 2023 | Accessibility Working Group Inclusion & Diversity Committee Diversity & Learning Officer |

# Implementation

Delivering the actions in our Accessibility Inclusion Action Plan is the responsibility of all Wannon Water employees. The Inclusion and Diversity Committee, together with the Accessibility Working Group, will work together to ensure organisational outcomes are met. Any employee is welcome to assist in this work on behalf of the organisation.

Wannon Water will continue to work towards a culture that demonstrates awareness, education and understanding of: people with disability; carers of someone with disability; and, those who may have individual accessibility requirements.

It is our commitment to implementing an Accessibility Inclusion Action Plan that achieves organisational outcomes. The Inclusion and Diversity Committee along with other working groups will lead the implementation of these activities.

# Legislative framework

In 2006, the Victorian Parliament passed the Disability Act 2006 (as amended). This act includes a provision making it mandatory for all government departments, statutory authorities and statutory corporations to develop Disability Action Plans (DAP).

The Victorian Government understands that people with disabilities, as a member of the community, should have access to a range of programs, services, facilities and employment opportunities that support quality of life.

While disability may be difficult to define, formal definitions such as those in legislation at state (Disability Act 2006) and federal level (Disability Discrimination Act 1992) reveal that disability is much wider than usually thought. The definition contained in the Disability Discrimination Act 1992 covers disabilities which are physical, intellectual, psychiatric, sensory and neurological. The definition also covers physical disfigurement and the presence of disease-causing organisms. This definition is applicable to a disability that currently exists, may exist in the future or is otherwise imputed to exist.

This Accessibility Inclusion Action Plan will help Wannon Water to continue to identify and, remove barriers to ensure that our customers, communities, employees and stakeholders have an opportunity to be part of our community, regardless of their abilities.

We will report on the implementation of this Accessibility Inclusion Action Plan annually consistent with Section 38 of the Disability Act 2006.

# Outcomes and Activities

The outcomes in this plan will ensure our work sites, facilities, vehicles and other amenities cater to a diverse range of employees, customers and community members. If we do not meet the needs of these groups, we will endeavour to change our ways. This may take time and resources, but we value the contribution that can be made.

We recognise that many employees spend a lot of time at work. It is imperative they enjoy their time in our workplace and create a positive environment for others. Through a range of awareness, education and training initiatives, we aim to create a workplace culture that is respectful and understanding of individual needs. We ask our employees to champion a vision for an inclusive and diverse workplace.

## Outcome 1: Provide services and facilities that are accessible to all

| Action | Task | Timeline | Responsibility |
| --- | --- | --- | --- |
| Access audit report to be undertaken, documenting the accessibility of Wannon Water’s corporate facilities | Audit to be completed and areas highlighted for priority | 21/22 (depending on level of COVID-19 restrictions) | Inclusion and Diversity Committee Branch Manager Corporate Services |
|  | Prioritise recommendations and list top five issues to be addressed | 21/22 (depending on level of COVID-19 restrictions) | Inclusion and Diversity Committee Branch Manager Corporate Services |
|  | Any implementation of actions to meet the Building Code requirements. Refurbish sites and accessibility to sites | To be determined based on value or priority works and budget/Price Submission. | Branch Manager Corporate Services |
| Ensure that all public information is accessible | Adopting accessible information principles and incorporating this in to updating a new webpage. Updating key public documents as needed. Incorporating accessibility in new customer publications. | Ongoing | Branch Manager Communication & Engagement |
|  | Customer publications, including simple summary versions where appropriate, will be made available via appropriate digital channels and utilise accessible audio and video where possible. | Ongoing | Branch Manager Communication & Engagement |
| Improve technology which aids and assists the accessibility of Wannon Water information | Improve the Wannon Water website, customer portal and social media platforms to WCAG 2.0 AA compliance, and identify any WCAG 2.0 AAA requirements that could be cost effectively implemented. | 2021-22 | Chief Information Officer IT Operations Manager Branch Manager Communications & Engagement |
|  | Digital Services respond to requests from employees for additional equipment and applications in supporting them in performing their role requirements (e.g., ergonomic keyboards, voice recognition software, etc). | Ongoing | Chief Information Officer |
| Ensure our procurement process supports accessibility | Include relevant accessibility criteria in tenders, contract management activities and internal requirements for workplace and customer technologies | 2021/22 - to be delivered as post of the procurement policy review. | Branch Manager Corporate Services |
|  | Create a diversity supplies action plan to ensure we either directly or indirect support disability employment | 2021/22 – To be delivered as part of the procurement policy review. | Branch Manager Corporate Services |

## Outcome 2: Reduce barriers to people with disability obtaining and maintaining employment with Wannon Water

| Action | Task | Timeline | Responsibility |
| --- | --- | --- | --- |
| Ensure Wannon Water has a recruitment process which is accessible for people with disability | Review the Recruitment and Appointment Procedure to ensure Wannon Water caters for people with disability through the recruitment and appointment process | December 2021 | Executive People & Resilience |
| Support the recruitment of people with disability to and within Wannon Water | Through traineeships and recruitment, employ people with disability | Annually (November) | Executive People & Resilience |

## Outcome 3: Promote inclusion and participation of people with disability in the community

| Action | Task | Timeline | Responsibility |
| --- | --- | --- | --- |
| Broaden our community feedback in relation to disability | Engage key disability stakeholder groups in line with our annual Accessibility Action Plan review | November 2021 | Accessibility Working Group |
|  | Have a representative from a disability related organisation present to the Wannon Water Inclusion and Diversity Steering Committee | 30 June 2021 | Executive Strategy & Innovation |
| Ensure Wannon Water community and stakeholder events are accessible to people with disability | Community and stakeholder events check lists developed to ensure that all events are designed, conducted and evaluated with the needs of people with disability in mind | 30 June 2021 | Branch Manager Communications & Engagement |
| Strengthen partnerships to promote greater accessibility, disability awareness and community cohesion. | Ensure that our partnership agreements include and are consistent with Wannon Waters approach to event accessibility | 30 June 2021 | Branch Manager Communications & Engagement |
|  | Wannon Water will endeavor to support community events, which are socially inclusive for communities, to include people with disability. | 30 June 2021 |  |

## Outcome 4: Achieve organisational culture change in attitudes and practices which discriminate against disability

| Action | Task | Timeline | Responsibility |
| --- | --- | --- | --- |
| Continue to build an inclusive culture by enhancing our employees level of disability awareness | Provide opportunities for employees to learn and understand the barriers of those with disability | Annually (December) | Diversity & Learning Officer Executive People & Resilience |
|  | Build disability awareness by promoting success stories, events and initiatives | Annually (December) | Diversity & Learning Officer Executive People & Resilience |
| Information to support the accessibility of Wannon Water workplace communications | Accessible information available for employees on support services (such as AUSLAN, Job Access, internal fact sheets) |  | Chief Information Officer Information Technology Operations Manager |
|  | Manager guidelines of accessible information available on waterSHED | Content to be uploaded once available/updated | Chief Information Officer Information Technology Operations Manager |
| Support the water industry Disability Employee Network (Waterable) | Wannon Water actively supports Waterable and promotes their activities to employees |  | Accessibility Working Group Inclusion & Diversity Committee |
| Where possible, ensure our learning and development programs are inclusive of people with disability | Training and event invitations to include questions on accessibility requirements | January 2021 | Executive People & Resilience |
| Ensure that employees are able to engage with people with disability | Wannon Water actively supports employees who choose to use their corporate volunteering leave with disability services | Ongoing | Executive Strategy & Innovation |

# Glossary

| Term | Definition |
| --- | --- |
| Accessibility | The quality or being able to be reached or entered. The quality or being able to easily obtain or use. The quality or being able to be understood or appreciated. |
| Auslan | The sign language of the Australian deaf community. The term Auslan is an acronym of Australian Sign Language. |
| Building Code | To protect the public health, safety and general welfare or occupancy of buildings or structures. |
| DAP | Disability Action Plan |
| Disability | A physical or mental condition that limits a person’s movements, senses or activities. A disadvantage or handicap, especially one imposed or recognised by the law. |
| DIAP | Disability Inclusion Action Plan |
| Job Access | The national hub for workplace and employment information for people with disability, employers and service providers. |
| MD | Managing Director |
| Reconciliation | A restoration of friendly relations. The actions of making one view or belief compatible with another. |
| Social Model of Disability | Where society’s attitudes, systems and constructs, rather than a person’s impairment that is restrictive to people with a disability. |
| WCAG | Web Content Accessibility Guidelines. There are three levels A(lowest), AA and AAA (highest) |
| WWEC | Wannon Water Engagement Cycle |

# Reference Documents

- Wannon Water People & Culture Policy Statement

- Wannon Water Inclusion and Diversity Management Plan

- Wannon Water Financial Inclusion Action Plan

- Wannon Water Social and Sustainable Procurement Strategy 2020 – 2023

- Victorian Government Disability Act 2006